## API Implementation Audit
Group ID | API Group Name | Feature / Endpoint Name | Method | Planned Route (API Plan) | Implemented Route (Darshan's Commit) | Status | Source File / Handler | Key Request Parameters | Response Model / Schema | Architectural & Comparison Notes
G0 | System Health | Gateway Root Welcome | GET | / | / | ✅ Implemented & Active | gateway/routes/health.py::root | None | JSON Dictionary | Returns service title, version, documentation URLs (/docs, /redoc), and core endpoint directory.
G0 | System Health | System Health Check | GET | /health | /health | ✅ Implemented & Active | gateway/routes/health.py::health_check | None | HealthResponse | Actively verifies 3 subsystems: PostgreSQL 18 connection pool, Redis message broker ping, and MinIO S3 bucket. Returns HTTP 503 if degraded.
G1 | Master & General | Master Paginated Tender List | GET | /api/v1/bids | /api/v1/bids | ✅ Implemented & Active | gateway/routes/bids.py::list_bids | limit, offset, search, status, is_expired | BidListResponse (items, total) | Sub-50ms query on PostgreSQL 'bids' table with indexed filters and total count. Supports live frontend card grids.
G1 | Master & General | Master Tender Dossier (Path) | GET | /api/v1/bids/{bid_no} | /api/v1/bids/{bid_id} | ✅ Implemented & Active | gateway/routes/bids.py::get_bid | bid_id (path, supports '/' and '_') | BidDetailResponse | The Master Dossier: Joins all 10 relational tables (scalars, items, consignees, schedules, atc_checklist, submissions, AI telemetry) in one ACID query.
G1 | Master & General | Master Tender Dossier (Query) | GET | /api/v1/bids/{bid_no} | /api/v1/bids/detail?bid_no=... | ✅ Implemented & Active | gateway/routes/bids.py::get_bid_by_query | bid_no (query param) | BidDetailResponse | Convenience query endpoint matching the master detail view for frontends that prefer query parameters.
G1 | Master & General | Original Scraped Raw JSON | GET | /api/v1/bids/{bid_no}/raw | Included in master detail (raw_data) | 🔄 Covered in Master Payload | gateway/routes/bids.py (db.get_bid_by_no) | bid_no | JSONB Document | The full unaltered raw scraped JSON is stored in PostgreSQL bids.raw_data and returned in master detail. Dedicated /raw slice endpoint planned.
G2 | Data Partitions | Lifecycle & Identity (Header) | GET | /api/v1/bids/{bid_no}/header | Included in master detail | 🔄 Covered in Master Payload | gateway/routes/bids.py | bid_no | BidDetailResponse (scalars) | Contains bid_no, ra_no, start/end dates, opening date, days remaining, status. Sub-route can be isolated for lightweight summary widgets.
G2 | Data Partitions | Buyer & Governance | GET | /api/v1/bids/{bid_no}/buyer | Included in master detail | 🔄 Covered in Master Payload | gateway/routes/bids.py | bid_no | Buyer fields in BidDetailResponse | Ministry, department, procuring organization, and office. Fully indexed and returned in master record.
G2 | Data Partitions | Items & Technical Specs | GET | /api/v1/bids/{bid_no}/items | Returned in BidDetailResponse.items | 🔄 Covered in Master Payload | gateway/routes/bids.py (bid_items) | bid_no | List[BidItemSchema] | Product catalogue items, quantities, and JSONB technical attribute specifications. Dedicated /items sub-route planned for supplier feeds.
G2 | Data Partitions | Logistics & Consignees | GET | /api/v1/bids/{bid_no}/consignees | Returned in BidDetailResponse.consignees | 🔄 Covered in Master Payload | gateway/routes/bids.py (bid_consignees) | bid_no | List[BidConsigneeSchema] | Consignee officer names, delivery addresses, cities, 6-digit pincodes, and delivery days. Dedicated /consignees route planned for logistics portals.
G2 | Data Partitions | Financials & EMD Guarantees | GET | /api/v1/bids/{bid_no}/financials | Returned in BidDetailResponse | 🔄 Covered in Master Payload | gateway/routes/bids.py | bid_no | Financial scalar fields | Estimated value, EMD requirement, EMD amount, advisory bank, and EPBG %. Dedicated /financials route planned for fintech/banking feeds.
G2 | Data Partitions | Policy & Relaxations | GET | /api/v1/bids/{bid_no}/policy | Returned in BidDetailResponse | 🔄 Covered in Master Payload | gateway/routes/bids.py | bid_no | Policy scalar fields | MSE purchase preference %, MSE relaxation flag, Startup exemption flag, Make in India (MII) preference.
G2 | Data Partitions | Mandatory Required Documents | GET | /api/v1/bids/{bid_no}/documents | Returned in BidDetailResponse.required_documents | 🔄 Covered in Master Payload | gateway/routes/bids.py (bids.required_documents) | bid_no | List[str] | Array of mandatory seller compliance certificates required by the buyer (e.g. Past Performance, Bidder Turnover, OEM Auth).
G2 | Data Partitions | ATC Compliance Checklist | GET | /api/v1/bids/{bid_no}/atc | Returned in BidDetailResponse.atc_checklist | 🔄 Covered in Master Payload | gateway/routes/bids.py (bid_atc_checklist_items) | bid_no | Dict[str, List[str]] | Categorized compliance checklist generated by Gemini AI across 8 legal and operational domains.
G2 | Data Partitions | Physical Offline Submissions | GET | /api/v1/bids/{bid_no}/submissions | Returned in BidDetailResponse.physical_submissions | 🔄 Covered in Master Payload | gateway/routes/bids.py (bid_atc_physical_submissions) | bid_no | List[Dict] | Hardcopy instruments (Demand Drafts, lab samples, banker checks) with deadlines and payee authority details.
G2 | Data Partitions | Evaluation Schedules | GET | /api/v1/bids/{bid_no}/schedules | Returned in BidDetailResponse.evaluation_schedules | 🔄 Covered in Master Payload | gateway/routes/bids.py (bid_evaluation_schedules) | bid_no | List[Dict] | Multi-lot bidding schedules with grouped line items and estimated schedule values.
G3 | Discovery & Filters | Bid Types Aggregation | GET | /api/v1/types | Planned discovery router | 📋 Planned Extension | gateway/routes/discovery.py (to be added) | None | TypesAggregationResponse | Aggregates total active tender counts and estimated budget values grouped by procurement bid type (Product, Service, BOQ, Custom).
G3 | Discovery & Filters | Procuring Organizations Directory | GET | /api/v1/organizations | Partially via /api/v1/bids?search=... | 📋 Planned Extension | gateway/routes/discovery.py (to be added) | min_bids, limit | OrganizationsDirectoryResponse | Directory of top procuring central and state government organizations with active tender counts and pipeline INR values.
G3 | Discovery & Filters | State-Level Procurement | GET | /api/v1/locations/states/{state}/bids | Planned discovery router | 📋 Planned Extension | gateway/routes/discovery.py (to be added) | state_name, limit | StateBidsResponse | Returns tenders originating in or delivering to specific states (e.g. Gujarat, Maharashtra, Rajasthan).
G3 | Discovery & Filters | Pincode Logistics Explorer | GET | /api/v1/locations/pincode/{pin}/bids | Planned discovery router | 📋 Planned Extension | gateway/routes/discovery.py (to be added) | pincode | PincodeBidsResponse | Discovers freight tenders requiring delivery to a specific 6-digit postal code based on bid_consignees index.
G4 | Search & AI | Semantic RAG Search (pgvector) | POST | /api/v1/search/semantic | /api/v1/bids/ask | ✅ Implemented & Active | gateway/routes/rag.py::ask_rag | query, top_k, bid_id, synthesize_answer | RagQueryResponse | Implemented by Darshan! Sub-5ms cosine similarity retrieval over PostgreSQL 18 gem_bid_chunks using 768-dim BGE embeddings + optional Gemini LLM answer synthesis.
G4 | Search & AI | Trigram Fuzzy Keyword Search | GET | /api/v1/search/keyword | Integrated in /api/v1/bids?search=... | ✅ Implemented & Active | gateway/routes/bids.py::list_bids | search (query string) | BidListResponse | Fuzzy text search matching bid numbers, organization names, and item categories in PostgreSQL.
G5 | Document Storage | Presigned Tender PDF Link (Path) | GET | /api/v1/documents/{bid_no}/pdf | /api/v1/bids/{bid_id}/pdf | ✅ Implemented & Active | gateway/routes/bids.py::get_bid_pdf | bid_id | HTTP 307 Redirect (Presigned S3 URL) | Implemented by Darshan! Generates secure 24-hour presigned MinIO S3 URL. Redirects client browser directly to MinIO without API server memory overhead.
G5 | Document Storage | Presigned Tender PDF Link (Query) | GET | /api/v1/documents/{bid_no}/pdf | /api/v1/bids/download-pdf?bid_no=... | ✅ Implemented & Active | gateway/routes/bids.py::get_bid_pdf_by_query | bid_no (query param) | HTTP 307 Redirect (Presigned S3 URL) | Convenience query endpoint for downloading tender PDFs with zero memory buffering.
G6 | Worker Tasks | Trigger On-Demand Scraper | POST | /api/v1/tasks/scrape-bid | /api/v1/bids/scrape-ondemand | ✅ Implemented & Active | gateway/routes/admin.py::trigger_ondemand_scrape | bid_no (or category, target_count) | TaskStatusResponse (HTTP 202) | Implemented by Darshan! Submits crawl task directly to Redis scraping_queue in 2ms. Supports single bid search or category crawling with custom count.
G6 | Worker Tasks | Check Celery Task Status | GET | /api/v1/tasks/{task_id} | /api/v1/tasks/{task_id} | ✅ Implemented & Active | gateway/routes/admin.py::get_task_status | task_id (path param) | TaskStatusResponse | Implemented by Darshan! Direct AsyncResult inspection of Celery task state (PENDING, STARTED, SUCCESS, FAILURE) and execution result payload.
G7 | Analytics & KPIs | System Health & Pipeline KPIs | GET | /api/v1/analytics/overview | Tracked in DB, planned dedicated route | 📋 Planned Extension | gateway/routes/analytics.py (to be added) | None | AnalyticsOverviewResponse | Aggregates total tenders scraped (61), ongoing active tenders, total pipeline INR value, item counts, and average EMD values.
G7 | Analytics & KPIs | AI & OCR Telemetry Audit | GET | /api/v1/analytics/ai-telemetry | Returned inside BidDetailResponse.ai_telemetry | 🔄 Covered in Master Payload | gateway/routes/bids.py (bids.ai_telemetry) | None | AITelemetryResponse | Tracks total token consumption, Gemini cost in USD/INR, and Mistral OCR page counts across pipeline runs.

## Data Partitions & Frontend Map
Partition ID | Partition Module Name | Database Source Table | Planned Sub-Route | Current Exposure in Darshan's Code | Target Frontend Component / B2B Commercial Feed | Next Implementation Step
P1 | Lifecycle & Identity | bids (scalar columns) | /api/v1/bids/{bid_no}/header | Exposed in GET /api/v1/bids/{bid_id} (id, bid_no, ra_no, start/end dates, remaining days) | Tender Header Card, Countdown Timer, Status Badge | Add isolated /header sub-route for fast card refreshes
P2 | Buyer & Governance | bids (ministry, dept, org) | /api/v1/bids/{bid_no}/buyer | Exposed in GET /api/v1/bids/{bid_id} (ministry_state_name, department_name, organisation_name) | Buyer Info Sidebar, Ministry & Department Breadcrumbs | Add isolated /buyer sub-route
P3 | Items & Specifications | bid_items (with specifications JSONB) | /api/v1/bids/{bid_no}/items | Exposed in GET /api/v1/bids/{bid_id} under 'items' array with full JSONB specs | Product Specs Tab, Supplier Match Feed, OEM Quoting Tool | Add isolated /items sub-route with category filtering
P4 | Logistics & Consignees | bid_consignees (officer, address, pincode) | /api/v1/bids/{bid_no}/consignees | Exposed in GET /api/v1/bids/{bid_id} under 'consignees' array | Consignee Map/Table Tab, Logistics Freight Quote Feed, Pincode Routing | Add isolated /consignees sub-route
P5 | Financials & Bonds | bids (estimated_value, emd_amount, epbg) | /api/v1/bids/{bid_no}/financials | Exposed in GET /api/v1/bids/{bid_id} root financial fields | Financial Overview Tab, Fintech Lending & Bank Guarantee (BG) Feed | Add isolated /financials sub-route with currency conversions
P6 | Policy Preferences | bids (mse_preference, startup_relaxation) | /api/v1/bids/{bid_no}/policy | Exposed in GET /api/v1/bids/{bid_id} policy flags | Eligibility Modal, MSME & Startup Qualification Calculator | Add isolated /policy sub-route
P7 | Mandatory Documents | bids (required_documents TEXT[]) | /api/v1/bids/{bid_no}/documents | Exposed in GET /api/v1/bids/{bid_id} under 'required_documents' array | Pre-Bid Document Checklist, Bidder Readiness Stepper | Add isolated /documents sub-route
P8 | ATC Compliance Clauses | bid_atc_checklist_items (8 domains) | /api/v1/bids/{bid_no}/atc | Exposed in GET /api/v1/bids/{bid_id} under 'atc_checklist' grouped by domain | Compliance Checklist Tab, Legal Risk Audit, Penalty Warning Alerts | Add isolated /atc sub-route with domain query filters
P9 | Physical Submissions | bid_atc_physical_submissions | /api/v1/bids/{bid_no}/submissions | Exposed in GET /api/v1/bids/{bid_id} under 'physical_submissions' array | Offline Submission Tracker, Sample Courier Alerts, DD Payment Details | Add isolated /submissions sub-route
P10 | Evaluation Schedules | bid_evaluation_schedules | /api/v1/bids/{bid_no}/schedules | Exposed in GET /api/v1/bids/{bid_id} under 'evaluation_schedules' array | Multi-Lot Bidding Matrix, Segmented Quoting Interface | Add isolated /schedules sub-route

## Commands & Schedulers Guide
Operation Scenario | Execution Method | Exact Command / Payload | Underlying Celery / Code Mechanism | Process Control: Start & Stop Behavior
Start 3 Worker Queues (Local) | PowerShell Script | .\start_workers.ps1 | Spawns 3 dedicated Celery processes in Solo mode (-P solo) on Windows: scraping_queue, document_queue, and atc_rag_queue. | START: Opens separate PowerShell worker windows. STOP: Run '.\start_workers.ps1 -Stop' to kill all Celery worker processes via Win32 WMI.
Start Workers + Periodic Scheduler | PowerShell Script | .\start_workers.ps1 -WithBeat | Spawns the 3 queue workers plus Celery Beat periodic clock daemon using tasks/beat_schedule.py. | START: Starts workers + Beat clock daemon. BEAT CYCLE: Automatically fires tasks.tier1_scraper.crawl_all_categories every 30 minutes. STOP: Run '.\start_workers.ps1 -Stop'.
Stop All Running Workers & Schedulers | PowerShell Script | .\start_workers.ps1 -Stop | Queries Win32_Process for 'tasks.celery_app' and forces immediate termination of all worker and beat PIDs. | Immediate termination of all background Python and Celery processes. Clean exit.
Run One-Shot Crawl via REST API (Single Tender) | REST API (FastAPI Gateway) | POST /api/v1/bids/scrape-ondemand Payload: {"bid_no": "GEM/2026/B/8113926"} | Calls tasks.tier1_scraper.scrape_single_bid.delay(). Searches specifically for that tender card, downloads PDF, and pipelines to Tier 2 and Tier 3. | START: Enqueues in ~2ms, returns Celery task_id. EXECUTION: Executes once for that single bid number. STOP: Finishes automatically upon completing the 3 worker tiers.
Run One-Shot Crawl via REST API (By Bid Type) | REST API (FastAPI Gateway) | POST /api/v1/bids/scrape-ondemand Payload: {"category": "Product Bid/RAs", "target_count": 5} | Calls tasks.tier1_scraper.scrape_category.delay(bid_type='Product Bid/RAs', target_count=5). Applies the category filter on GeM portal. | START: Enqueues in ~2ms, returns task_id. EXECUTION: Crawls until 5 un-seen tender cards are processed. STOP: Terminates automatically when target_count is reached.
Check Task Status via REST API | REST API (FastAPI Gateway) | GET /api/v1/tasks/{task_id} | gateway/routes/admin.py::get_task_status inspects Celery AsyncResult. | Returns real-time status: PENDING -> STARTED -> SUCCESS (with tender ID & chunk count) or FAILURE.
Run One-Shot Crawl via Python CLI (Single Tender) | Python Command | .\venv\Scripts\python -c "from tasks.tier1_scraper import scrape_single_bid; print(scrape_single_bid('GEM/2026/B/8113926'))" | Direct synchronous invocation of the crawler function without requiring Celery daemon. | Runs directly in foreground. Crawls the target bid, streams to MinIO, enqueues Tier 2, and exits cleanly.
Run One-Shot Crawl via Python CLI (By Bid Type) | Python Command | .\venv\Scripts\python -c "from tasks.tier1_scraper import scrape_category; print(scrape_category('Product Bid/RAs', target_count=2))" | Direct synchronous invocation of category crawler. | Opens browser, selects category filter 'Product Bid/RAs', downloads up to 2 un-seen tenders, closes browser, and exits.
Launch FastAPI REST Gateway (Local) | Uvicorn ASGI Server | .\venv\Scripts\uvicorn gateway.main:app --host 0.0.0.0 --port 8000 --reload | Launches FastAPI Gateway with PostgreSQL connection pool (minconn=2, maxconn=10), MinIO S3 integration, and telemetry middleware. | Runs on http://localhost:8000. Interactive docs available at /docs and /redoc. Stop with Ctrl+C.
Run Production Stack (Docker / Dokploy) | Docker Compose (VPS) | docker compose -f docker-compose.prod.yml up -d | Spins up the full 7-service enterprise stack: redis, worker-scraper, worker-document, worker-atc, celery-beat, fastapi-gateway, and flower. | START: Runs continuously in background with healthchecks and restart policies. STOP: 'docker compose -f docker-compose.prod.yml down'.